Participatory Agriculture and Climate Transformation (PACT) Programme

Terms of Reference (ToR) on Poultry and Banana

Value Chain Analysis

NOVEMBER 2024

ADDIS ABABA

ETHIOPIA

Table of Contents

1.	INTRODUCTION	0

2.	GENERAL OBJECTIVES OF THE ASSIGNMENT	1

3.	METHODOLOGICAL REQUIREMENTS FOR THE POULTRY AND BANANA VCA	3

3.1.	Sample frame	3

3.2.	Sample size	3

3.3.	Probability sampling	3

3.4.	Data quality control	3

3.5.	Analysis and report	4

3.5.1. Analysis	4

3.5.2. Report	4

4.	DETAILED LIST OF ACTIVITIES, SCHEDULE AND DELIVERABLES	4

4.1.	List of activities	4

4.2.	Schedule of Deliverables	5

5.	COMPETENCIES REQUIRED	5

5.1.	Key staff	5

5.2.	Non-Key staff	7

6.	SUBMISSION OF THE PROPOSAL	8

6.1.	Evaluation points of the technical and financial Proposal:	8

6.1.1.	Technical proposal:	8

6.2.	Proposal Evaluation Criteria	9

7.	COMMUNICATION AND CONFIDENTIALITY	9

# INTRODUCTION

The MoA - PACT Programme was jointly designed by GoE and IFAD. The Programme’s rationale is premised on the fact that, the combination of Ethiopia’s expected economic recovery and a high population growth rate imply an increase in demand for agricultural products. The need to increase local production of food, especially wheat and oilseeds, and improve rural households’ resilience to shocks has never been greater. Although IFAD has supported the country’s efforts to boost the productivity of selected agricultural commodities through different investments to address the underlying constraints, Ethiopia remains dependent on rain-fed agriculture. The Programme’s goal is ‘to contribute to inclusive and equitable poverty reduction and improved resilience of the target rural households.’ The Programme Development Objective (PDO) is to ‘enable 150,000 rural households (men, women, youth and PWDs) in selected kebeles to sustainably improve incomes, food and nutrition security and build resilience to shocks. The Programme will be implemented over a seven-year period.

MoA - PACT brings together businesses, governments, farmers, communities, and civil society to build sustainable governance models in landscape approaches. These multi-stakeholder coalitions create areas where agricultural products are grown sustainably (Production), forests and natural resources are safeguarded (Protection), and communities thrive (Inclusion).

The Programme’s Development Objective will be achieved through the effective implementation of two technical components and a third component that will focus on augmenting the capacity of communities, and institutions, and contributing to a conducive policy environment towards programme implementation. Job creation for young women and men, including persons with disabilities, will be the main focus of all investments in the MoA - PACT Programme.

A value chain is the full range of activities - including design, production, and distribution - required to bring a product or service from conception to its final market destination. A pro-poor value chain development intervention promotes inclusiveness and empowerment of poor people in a value chain. The Market Map is made up of three interlinked components: Value chain actors (Input suppliers, farmers, traders, consumers), Enabling environment (infrastructure and policies, institutions and processes that shape the market environment), and Service providers (the business or extension services that support the value chains’ operations).

Value chain analysis (VCA) plays an important role in transforming agricultural commodities from raw materials to end products demanded by consumers. There are several stakeholders involved in the agricultural commodity value chains and the partitioning of gains among the stakeholders along the chain is often debated and analyzed. Input suppliers, farmers/pastoralists, processors, wholesalers, retailers, big retail chains, and consumers are major actors in the value chain. Poultry and banana are among the prioritized commodities to conduct VCA which is essential for identifying opportunities and constraints in production and marketing, as well as for exploring potential improvements towards sustainable value chain development.

The poultry sub-sector in Ethiopia offers significant opportunities for agribusiness, being a critical part of the culture and practice across various socioeconomic groups. It plays a vital role in reducing malnutrition, and poverty, and promoting economic growth, contributing to the country’s overall development (Dessie et al., 2003; Wilson, 2010). With rising demand for high-quality protein driven by population growth and urbanization, poultry production is increasingly important for food security and income generation.

Ethiopia's poultry systems include traditional family production, improved family production, and specialized production. The total chicken population is approximately 59.5 million, predominantly indigenous breeds, which are less productive than exotic breeds (CSA, 2019). Challenges such as ineffective extension services, high input costs, and inadequate infrastructure hinder the development of the commercial poultry industry, which remains largely subsistence-oriented.

To achieve growth, a strategic transition from traditional to improved poultry systems is essential. Although the Ethiopian Livestock Master Plan (LMP) aimed for an exportable surplus of poultry meat by 2020, local demand has outstripped supply, making exports impractical (de Gonçalves, 2005). The government’s Ten-Year Perspective Plan emphasizes poultry development, highlighting the need for a comprehensive Poultry Development Strategy to harness the economic potential of poultry farming.

Bananas (Musa spp.) are important fruits in the tropics and subtropics. Ethiopia is among the tropical countries where its vast arable land is suitable for banana cultivation. Banana has important socioeconomic role in food security and income generation for the rural communities in the country. Despite its importance, the national average yield of banana is estimated at 8.0 t/ha which is far less than the world average 22.6 t/ha (FAOSTAT, 2019), and the productivity of banana in 2020/21 cropping season was about 9.4 t/ha (Central Statistical Agency of the Ethiopia 2021). The low productivity of banana is mainly attributed to the limited provision of production technologies such as improved varieties and crop management practices, diseases and insect pests, poor postharvest handling and marketing, and insufficient support from the extension system (Dagnew et al., 2021)

The VCA will follow a value chain mapping and analysis approach that describes in detail the poultry and banana value chain functions, value chain actors (women and men producers, cooperatives, traders, agro-dealers, processors like Integrated Agro Industry Parks (IAIPs) …), value chain enablers and value chain supporters. To enhance meaningful participation of women, youth, PWDs, and other socially marginalized groups; the value chain assessment will be gender and youth-responsive and will take different socio-economic profiles into account, including persons with disabilities, and pastoralists' alternative livelihoods. Since MoA - PACT intervenes in food-insecure woredas, the value chain assessment will be a pro-poor value chain analysis in the identified and selected landscapes of the programme.

Within the scope of this holistic approach, PACT programme seeks to support the development of a viable agricultural value chain for poultry and banana. With this ToR, the PACT programme aims to identify and select a partner who can conduct a VCA on poultry and banana across the selected programme intervention areas.

# GENERAL OBJECTIVES OF THE ASSIGNMENT

The overall objective of this assignment is to conduct a Value Chain Analysis (VCA) on Poultry and banana within the PACT program intervention areas so as to identify potential opportunities and challenges, as well as to propose solutions for the challenges identified.

The specific objectives are:

- Plan and conduct a VCA focusing on:

  - Identification of major value chain actors, (existing input suppliers, producers, traders, agents, processors, service delivery actors such as finance and transport, consumers, and others in the project sites) and assess current production level and potential in the smallholder beneficiaries;

  - Conduct value chain mapping and the mapping should also analyze gender-specific roles and functions along the different stages of the poultry and banana value chain, from primary production at the household level (who does what?) up to the marketing level (who participates in market transactions)

  - Identification of the enabling environment including local market structure and key risks/barriers in the enabling environment (e.g., security issues or policies affecting market access), taking into consideration specific gender, youth, and PWDs-related considerations (e.g., mobility, proximity, and bargaining constraints), value chain frameworks, business environment & policy, improving access to business development services and value chain governance. Institutional constraints for effective participation of women and men in the value chain, including what hinders/opportunities for participation in and benefit from engagement in the value chain.

  - Identification of specific opportunities and challenges for women, youth, women-led cooperatives, and PWD to be involved both as producers and service providers as well as to expand/upgrade their functions and production practices in these value chains. The analysis should also focus on how gender power dynamics and discriminatory gender norms influence women’s capacity to participate and/or upgrade their activities in the value chains, and participate in marketing decisions, outputs, and income. This aspect looks at i) women’s and men’s roles and time use outside of the value chain as it determines the available time and work burden; ii) Access to and control over production, income, and productive assets (land, livestock and all relevant capital items specific to the context)

  - Assessment of the presence and the role of existing types of groups and producers’ groups across different nodes of the poultry and banana value chains, as a way to improve women's and men's positions and benefits from value chain inclusion. Assess gender dimensions of such groups such as composition, women's inclusion, and roles.

  - Assess marketing margins, conduct economic analysis and profitability of the value chain and potential impacts on environmental and climate impacts and empowerment of women.

  - Identification of possible new links that can be created and existing links that can be improved; also looking at new market linkage opportunities for women, youth, PWDs, and other socially marginalized groups of the community, producers, and suppliers.

  - Analysis of the supporting functions that are required to make the value chain work, including both existing and missing support functions e.g., infrastructure, information, finance, and market requirements such as quality and other standards, conditions for delivery, prices and related services; assess gender dimension of these supporting functions (e.g., specific issues/opportunities in women’s access to finance)

  - Identify strategies to make the value-chain nutrition-sensitive (e.g., leveraging opportunities to promote safe production practices, nutrition-sensitive extension, diversified production and market channels, etc.)

  - Identification of strengths, weakest linkages, bottlenecks (challenges), opportunities, threats, and upgrading in the poultry and banana value chains.

- Key Deliverables:

- Inception report explaining concept, methodology, and timeline.

- Value chain mapping, identification of major and support activities, cost and value analysis, competitive advantage, and strategic recommendations independently for poultry and banana.

- Prepare and submit an independent final VCA report for poultry and banana.

# METHODOLOGICAL REQUIREMENTS FOR THE POULTRY AND BANANA VCA

The PACT Programme intends to conduct a value chain analysis to obtain qualitative and quantitative data that will enable to identification of opportunities, challenges, and possible entry points in the poultry and banana value chains. The scope of the services required under this Terms of Reference includes the collection of data from all value chain actors including the Household level by using focus group discussions with both women and men farmers, youth and PDWs, farmers/pastoralists organizations of different kinds, and composition (e.g., women-only or mixed), and financial institutions, business organizations, consumers and other related actors. The proposal should include an appropriate methodology for primary data collection, data collection tools (e.g., interviews with value chain actors, observing the value chain path, and key informant interviews), and analysis methods and mechanisms that will be used to conduct the poultry and banana VCA.

## Sample frame

The sample frame is the list of all the units in the desired population, from which random samples of units are selected to build the VCA samples. Hence, the firm should understand the nature of the programme and group of beneficiaries to develop the sample frame which is pertinent to the PACT programme.

## Sample size

The sample size calculation aims at determining how many observations are enough for the analysis. Power calculations have to be carried out in the preparation phase of the analysis and allow building a sample to credibly detect a given effect size (size of the impact that you expect to have from a project). The program recommends the use of the World Bank power formula (World Bank. 2007). If the firm selects a different formula should come with justification.

## Probability sampling

Probability sampling refers to the sampling method in which all the members of the population have an equal chance to be a part of the sample and it uses random selection to select the sample within the desired population. The firm should use the probability sampling method to give an equal chance for all beneficiaries or HHs. This program will work on regions that have different geographical locations and cultures. Hence the firm will propose desirable probability methods for this assignment.

## Data quality control

Data quality assurance is a critical step when collecting and storing data. some key points on the importance of data quality review:

- Error Checking

- Data Completeness

- Data Consistency

- Data Integrity

- Sufficient Time Allocation

- Iterative Process

- Documentation

Data-quality checks should be implemented while collecting the data rather than ex-post as in the case of paper-based surveys by using electronic devices for the data collection. Hence the firm may use data collection by electronic tool for instance kobo tool or other related data collection tools to enable on-spot data quality checks.

## Analysis and report

### 3.5.1. Analysis

The VCA method/tool is vital to find the intended results. The firm will present the type of analysis expected appropriate for this assignment. The firm also explains how the estimation, interpretation and presentation of the results should be done.

### 3.5.2. Report

Once the surveys have been conducted and their quality controlled, the analysis of the results should be presented in a report. The report summarizes the conclusions emerging from the analysis and includes the following elements:

- the description of the dimension of the value chain, methodology, and approaches used

- the questionnaire

- the list of villages/communities surveyed

- the results of the survey

- the analysis and interpretation of the results including Economic analysis of the poultry and banana value chains and analysis of constraints and setting the strategy.

The survey finding report should be provided to the PCMU.

# DETAILED LIST OF ACTIVITIES, SCHEDULE AND DELIVERABLES

The firm will work in close collaboration with the subject matter experts from the PCMU. The VCA activities will be conducted under the supervision of the PCMU. The firm will be responsible for the development and supervision of all phases of data collection and analysis which includes designing the data collection methodology, instruments, and processes.

## List of activities

Phase 1 - Inception phase

- Review the relevant documents on poultry and banana VCA

- Develop the detailed plan and work schedule to conduct the poultry and banana VCA to gather information from the relevant stakeholders at the national, regional, woreda, and kebele levels

- Develop the survey questionnaire based on the ToR provided by the project.

- Develop the sampling design and data analysis tools.

- Develop interview guides and instructions for field staff.

Phase 2- Survey instrument development

- Developing the Questionnaire.

- Training of interviewers for the pilot survey.

- Developing an appropriate data management system with adequate quality controls.

- Organize an inception workshop to discuss with PCMU and relevant stakeholders on the implementation and execution of the assignment.

The PCMU shall be responsible for providing key background documentation to the firm (PDR, PIM, the preliminary listing of potential beneficiaries, secondary data, etc).

Phase 3 – Fieldwork Activities

- Hire staff and survey enumerators with the necessary skills in local languages spoken in the programme intervention areas and train them to familiarize them with the subject matter, the relevant information required to be collected, and the survey questionnaire to collect data from primary sources.

- Administrative approval from necessary authorities.

- Conduct the quantitative and qualitative data collection at the appropriate level of analysis across all value chain actors.

- Supervise data entry, verification of data quality for analysis and data cleaning should also be performed.

Phase 4 - Data Processing, Analysis, and Final Report Preparation

- Clean, analyze, and interpret the data

- Prepare and submit a brief independent VCA poultry and banana reports to PCMU.

- Submit the final VCA reports after receiving comments and suggestions from PCMU.

- Prepare a workshop to familiarize the findings to the PCMU and partners.

- Submit the final and refined version of the value chain analysis reports to the PCMU.

- Survey questionnaires, TOR, minutes, pictures and participants' signatures, list of contacts has to be annexed to the VCA report.

The firm should deliver all the material in electronic and hard copy format.

## Schedule of Deliverables

The expected tasks for the firm should be performed under a mutually agreed schedule. Final deliverables should be submitted according to this schedule and within the limits of the contract duration. The assignment is expected to be completed within four months starting from the contract has been granted, with specific deliverable milestones and timelines that the firm must be aware of and work towards to ensure the successful and timely completion of the VCA. The provided timetable is an important reference point for the firm to manage the assignment effectively.

Table 1 Deliverables of Outputs in the Value Chain Analysis

| No | Output | Time (Submitted) |
| --- | --- | --- |
| 1 | Submit and present the inception reports | 10 days after the signing of an agreement |
| 2 | Inception workshop | 5 days after inception report submission |
| 3 | Fieldwork (Data collection) | 30 days Data will be collected - Immediately after the inception report has been approved |
| 4 | Data analysis and submission of the first draft reports to FPCMU | 30 days after data collection |
| 5 | Incorporating comments and suggestions from PCMU. | 20 days after the first draft |
| 6 | Report and conduct stakeholders’ workshop | 10 days after the revision of the first draft |
| 7 | Submit the final and refined version of the value chain analysis reports to the FPCMU. | Within 15 days after the workshop |

# COMPETENCIES REQUIRED

## Key staff

The proposed team should consist of a reasonable number of qualified and experienced professionals having a proven track record in designing and implementing socio-economic and VCA studies and having a good depth of understanding of value chain development, agricultural development, nutrition, gender & social inclusion. The Consulting firm is expected to propose a survey coordinator/Team Leader and an appropriate number of experts, field supervisors, enumerators, and support staff.

Table 2. Suggested List of key staff of the Consultancy Team

| No | Role | Specialization | Minimum Qualification | Experience |
| --- | --- | --- | --- | --- |
| 1 | Team Leader/ Study Coordinator | Advanced degree in economics, statistics, agricultural economics, agribusiness, and value chain management or related field. | BSc . but MA/M.Sc or Ph.D. preferred | - At least 12 years of relevant experience in conducting value chain analysis and development, large quantitative survey implementation and analysis, experience in household and agricultural data collection and analysis required, ability to coordinate teams and ensure timely reporting. - The study coordinator/Team Leader will be in charge of coordinating the planning and implementation of the analysis and ensuring that the work is conducted following the highest professional standards. The individual will be in charge of ensuring that the quality control and supervision mechanism in place for the survey is effective, manage the data collection team and ensure that each member performs their specific scope of work. - Experience in working on gender-related consultancy services |
| 2 | Agribusiness and value chain management or Socio-economic expert | Agribusiness, value chain management, cooperative/ agricultural marketing/ agricultural economics or related fields | B.Sc but M.Sc. preferred | - At least 10 years of experience in value chain management/ development, agribusiness management, primary cooperative/unions, marketing of agricultural products, value chain and market linkages, etc., is desirable. A good command of English and knowledge of the Ethiopian condition is an advantage. - Experience in working on gender related programs and conducting gender related value chain analysis - The agribusiness/ value chain management/ socioeconomic expert will be responsible for considering all value chain related issues such as market analysis, supply chain, value chain mapping, identify bottlenecks in the value chain and propose solutions to improve efficiency and reduce costs and other related activities. |
| 3 | Animal production or poultry production expert | Animal production/ poultry production or related fields | BSC but M.Sc. preferred | - At least 10 years of experience in animal production/ poultry production is highly desirable. A good command of English and knowledge of the Ethiopian condition is an advantage. - The expert will be responsible for assessing current production level and potential in the smallholder beneficiaries; the poultry value chain mapping, identifying key bottlenecks and propose possible solution and other related activities |
| 4 | Horticulture or fruit production expert | Horticulture/fruit development fields | BSC but M.Sc. preferred | - At least 10 years of experience in horticulture/ fruit development is highly desirable. A good command of English and knowledge of the Ethiopian condition is an advantage. - The expert will be responsible for assessing current production level and potential in the smallholder beneficiaries; the banana value chain mapping, identifying key bottlenecks and propose possible solution and other related activities |

## Non-Key staff

Figure 3. Suggested List of the non-key staff of the Consultancy Team

| No | Role | Specialization | Minimum Qualification | Experience |
| --- | --- | --- | --- | --- |
| 1 | Gender expert | Qualified in gender studies/rural development and family sciences and related field of studies | BA/BSc but MA/M.Sc. preferred | - At least 10 years of experience in gender studies/RDFS/ and related development studies is highly desirable. A good command of English and knowledge of the Ethiopian condition is an advantage. - A Good level of experience in conducting gender analysis in economic sectors, a good grasp of gender equality and women’s empowerment dynamics in the country - The expert will be responsible for identification of specific opportunities and challenges for women, youth, women-led cooperatives and PWD to be involved both as producers and service-providers as well as to expand/upgrade their functions and production practices in these value chains. - The expert will follow up and suggest possible solutions on how gender power dynamics and discriminatory gender norms influence women’s capacity to participate and/or upgrade their activities in the value-chains, and other related activities. |
| 2 | Nutrition Expert | Rural Development and Family Science, human nutrition, food science & technology expert | BA/BSc but MA/M.Sc. preferred | - At least 10 years of experience in mainstreaming nutrition into development programs is a requirement. A good command of English and knowledge of the Ethiopian condition is an advantage. - The expert will be responsible for identifying strategies to make the value-chains nutrition sensitive (e.g., leveraging opportunities to promote safe production practices, nutrition-sensitive extension, promoting diversification and diversified market channels etc.) and other related activities. |
| 3 | Data entry and Analysis expert | Computer science, statistics and related fields | BSC but M.Sc. preferred | - At least experience of 7 years with large survey data sets and data entry software required. - The expert will be responsible for ensuring accurate data entry, management, analysis and insightful interpretation, |
| 4 | Survey Supervisors (5) | Agribusiness, economics, business administration, or a related field. | BA/BSc but MA/M.Sc. preferred | - At least 8 years of experience in agribusiness, supply chain management, or related areas. - Demonstrated experience in project management, including leading teams and managing budgets. - Hands-on experience in agricultural production, market analysis, or rural development can be beneficial - Strong analytical and problem-solving skills. - Proficiency in data analysis software and tools (e.g., Excel, SPSS, R). - Excellent communication and interpersonal skills. - Leadership and team management capabilities |
| 5 | Survey enumerators (25) | Agriculture and related fields are preferred | Diploma but BSc. preferred | - At least 8 years’ experience. Preference will be given to candidates with experience in quantitative and qualitative data collection in rural Ethiopia. - Experience in data collection, field research, or survey administration is highly desirable. - Familiarity with agricultural practices and local market conditions relevant to the value chain being analyzed. |

# SUBMISSION OF THE PROPOSAL

## Evaluation points of the technical and financial Proposal:

The assignment evaluation points are 80% for technical proposal & 20% for financial proposal

## Technical proposal:

In submitting their technical proposal, the consultants must: Carefully review and comment on the Terms of Reference, recommending potential refinements where necessary, including making such recommendations as deemed appropriate to enhance the quality of the assignment and outputs/deliverables.

Submit a detailed methodology, sampling techniques, sampling size, and work plan including a schedule, the name, professional status, and biographic data of the professional key team members' CVs, including detailed work experience and education.

Copy of the following:

- Renewed trade license

- TIN

- Tax clearance

- VAT registration

## Proposal Evaluation Criteria

    - Technical Proposal Evaluation Forms (80%)

| No | Evaluation Methodology and Criteria. | Allocated Points |
| --- | --- | --- |
| 1 | Conceptualization of the TOR- Self-reflection and clarity on the purpose/ objectives and the scope of the task (Understanding of the core issues of the assignment), mobilization and staffing of non-key experts, clarity and adequacy of the work plan | 40 |
| 2 | key experts | 50 |
| 3 | Experience of the organisation | 10 |
|  | Total point | 100 |

    - Financial Proposal evaluation (20%)

The consultant should prepare a detailed budget for the activities or phases in the work plan. Price should cover items including local transportation, professional fees, per diem and other expenses, payments for interviewers, data processors, and secretarial services, applicable tax, etc. This should be presented in a separate envelope and indicate the proposed cost breakdown. The financial proposal will be opened only for those entities whose technical proposals achieved the minimum technical threshold of 70% and are determined to be compliant. Non-compliant proposals will not be eligible for further consideration.

P.S: This shortlisting stage does not require technical and financial proposals.

# COMMUNICATION AND CONFIDENTIALITY

All queries regarding the details in this ToR must be submitted in writing to the following address:

Ministry of Agriculture (MoA)

Procurement Executive

Block. A – Second Floor

Bole Sub-City, Around Gurd Shola, near EIAR or Behind the Ministry of Trade and Regional Integration.

Addis Ababa, Ethiopia

The Ministry reserves the right to amend or cancel all or part of this bid consultancy service at any time. The documents provided by or on behalf of the Ministry will be handled with confidentiality. The Service provider will also impose a confidentiality duty on any parties it engages. Any breach of the duty of confidentiality by the Service provider or its engaged third parties will give the PACT programme grounds for exclusion of the Service provider without requiring any prior written or verbal warning.

Institutions/structures refer to broad formal frameworks like policies, laws, regulations, markets and the implementing structures. Institutions/structures also encompass informal institutions like social and gender norms, attitudes, values, customs, religion and the various structures through which these are upheld and practiced in society.